## Sheet1
PROPOSED ADDITIONS AND ALTERATIONS OF AN EXISTING 2-STOREY DETACHED DWELLING HOUSE WITH AN ATTIC ON LOT 99470K MK17 AT 19 CAMBORNE ROAD (NOVENA PLANNING AREA)
BILL NO. 1 - PRELIMINARIES
Item | Description | Amount S$
A | TENDER DOCUMENTS
The Contractor shall check and ensure he has received the full and complete set of tender
documents:
B | DEFINITIONS
Where the followings terms are used in the Contract, they refer to the following firms,
corporations or persons, including where the context requires, their authorised representatives: Employer : Mr Ling Peng Meng 19 Camborne Road Singapore 299855 Employer’s Representative : To be Advised
Architect : Ong & Ong Pte Ltd 510 Thomson Rd #11-00 SLF Building Singapore 298135 Quantity Surveyor: OHA Global Pte Ltd 1 Sims Lane #04-08 One Sims Lane Singapore 387355 Unless the context otherwise requires, where the following terms are used in the Contract, the definitions given below shall apply: “Approved” or “Selected” shall mean the approval of or selection by the Employer’s Representative. “Articles of Agreement” means the Agreement entered into between the Employer and the Contractor for the design, construction, completion and maintenance of the Works. “Authority” or “Authorities” means any government department or authority or statutory body that has jurisdiction with regard to the design and to the Works or to whose systems the same are or will be connected either temporarily or permanently or whose services will be used in connection with the Works. “Conditions” means the REDAS Design and Build Conditions of Contract (4th Edition) published by the Real Estate Developers' Association of Singapore, the Appendices and Option Module thereto and the Supplemental Conditions (if any).
| TO COLLECTION: | $ -
A | DEFINITIONS (Cont’d)
“Contract Documents” means the Articles of Agreement, the Conditions including the
Appendices, the Option Module and the Supplemental Conditions (if any), the Employer’s Requirements, the Employer’s design drawings, the Contract Sum Analysis (including the Schedule of Rates), the Contractor’s Proposals (including the Specifications and Contract Drawings) and any other documents forming part of the Tender, the Letter of Acceptance and such other letters and documents as the parties may expressly identify in writing and agree as forming part of the contract, including those listed in Appendix 4 to the Conditions. “Contract Drawings” means the drawings prepared by or on behalf of the Contractor which are contained in the Contract, including those provided in the Contractor’s Proposals and any modifications or additions thereto or additional drawings as may from time to time be approved in writing by the Employer’s Representative pursuant to the terms of the Contract and identified as Contract Drawings. “Contract Sum” means the lump sum set out in the Letter of Acceptance and shall be fixed subject only to adjustments expressly provided for in the Contract. Unless the context otherwise requires, where the following terms are used in the Contract, the definitions given below shall apply (cont'd): “Contractor” has the meaning ascribed to that term in the Conditions. “Equal” and “Approved” shall refer to Plant, Materials or workmanship equal in all respects to that specified and which have been approved by the Employer’s Representative. “Payment Claim” and “Payment Response” shall refer to the terms “payment claim” and “payment response” as defined in the Building and Construction Industry Security of Payment Act 2004. “Schedule of Rates” or “Schedule of Works” means the documents described as such and which form part of the Contract Sum Analysis. “Site” means the premises located at lot 02493M at 32 Woodlands Terrace, Singapore 738452 and the land and other places on, in, under, over or through which the Works are to be executed or carried out or any other lands or places as may be specified in the Contract as forming part of the Site. “Specifications” means all specifications contained in the Contract as specified in the Contractor’s Proposals including any modifications or additions thereto or additional specifications as may from time to time be approved in writing by the Employer’s Representative pursuant to the terms of the Contract and identified as Contract Specifications. “Sub-contractors” and “sub-contracts” shall include suppliers and supply contracts, where the context requires.
| TO COLLECTION: | $ -
A | DEFINITIONS (Cont’d)
“Works” means the Works as defined in the Articles of Agreement and the Conditions and
which are briefly described in these Preliminaries and shown and/or described in the Contract including the Employer’s design drawings, the Contract Drawings and the Specifications. The English language shall be used for the purpose of the Contract and the Contractor shall ensure that all of his supervisory staff on Site and the senior head office personnel assigned to the Contract are able to speak, read and write the English language. Words in the singular shall include the plural and words in the plural shall include the singular according to the context. Words importing the masculine gender shall include the feminine or neuter genders, as the case may require.
B | CONDITIONS OF CONTRACT
This Contract is a LUMP SUM CONTRACT executed in accordance with the "REDAS
Design and Build Conditions of Main Contract (4th Edition)" published by the Real Estate Developers’ Association of Singapore (REDAS). The Contractor may make arrangement with OHA Global Pte Ltd to inspect a copy at their office located at 1 Sims Lane, #04-08, Singapore 387355. This Contract shall be based on a LUMP SUM TENDER and is not subject to adjustment in respect of fluctuation of labour and material cost including cement and steel reinforcement. This LUMP SUM CONTRACT shall include: a. All the Works as shown in Tender drawings and documents. b. All Appendies including Contract Sum Analysis (Appendix 5). c. Schedule of Unit Rates and Daywork Rates. Unless otherwise expressly provided, the Contract Sum Analysis and the prices in the Schedule of works and Schedule of Rates shall be inclusive of all ancillary and other works and expenditure whether separately or specifically mentioned or described in the Contract Document or not or which are either indispensably necessary to carry out and bring to completion of the works described in the Contract Document or which will contingently become necessary to overcome difficulties before completion.
| TO COLLECTION: | $ -
A | CONTRACTOR TO VISIT SITE
The item of works described in the Schedule of works must not be taken as being complete.
The Contractor shall visit the site and study the tender drawings to satisfy himself to the full extent and character of the Works to be executed and completed in this Contract. The Contractor shall check the actual levels against those shown on drawings and in the event of any discrepancy shall immediately notify the Employer’s Representative. No consideration will be granted in terms of monetary compensation and/or extension of time to the agreed Contract Period for misinterpretation of unforeseen difficulties for which provisions have not been made in the pricing of the tender. This will in no way relieve the Contractor's contractual responsibilities from executing and completing the Works by the relevant Date of Completion. Should the Contractor elect to use or infringe upon any land outside of the site boundary without any legal permit, he shall be solely responsible for any claims and/or fines imposed on him by the relevant local Authorities and/or third parties in connection therewith and make good any damages at Contractor's own expense.
B | PROGRAMME
The Contractor shall furnish a programme showing the start date and completion date of the
following Works: a. Proposed sequence of operations of his works. b. Works of individual Sub-contractors and Suppliers. c. Submission of samples and equipment from the Contractor, the Sub-Contractors and Suppliers for approval. d. Delivery dates of each material and equipment to the site from the Contractor, Sub- Contractors and Suppliers. e. Submission of design and shop drawings for approval. f. Testing and Commissioning of services. g. Applying and obtaining Temporary Occupation Permit (TOP) and Certificate of Statutory Completion (CSC). h. All other essential works not listed above and/or any other works specified by the Employer’s Representative. The Contractor shall submit the programme to the Employer’s Representative for approval within fourteen (14) calendar days after the award of the Contract. The programme shall be updated as and when necessary, with the Employer’s Representative's approval but the agreed or extended completion date shall not change.
| TO COLLECTION: | $ -
A | LICENSING OF BUILDERS AND IMPORTERS FOR ESSENTIAL CONSTRUCTION MATERIALS
The Contractor shall hold a valid General Builder License Class 1 issue by BCA. The Contractor shall maintain validity of his License throughout the Contract Period and Maintenance Period. If the Contractor fails to renew his License by the date of expiry or his License has been revoked by BCA, the Employer shall be entitled to terminate the employment of the Contractor. The effects of such termination shall be the same as clause 30.3 of the Conditions. The Contractor shall ensure that all specialist subcontractors engaged by him hold the valid and relevant Specialist Builder License from BCA where applicable. The Contractor shall ensure all essential construction materials (i.e. concreting sand and granite) are imported and supplied by licensed importers, whether through himself or his subcontractors or suppliers
B | CONSTRUCTION REGISTRATION OF TRADESMEN SCHEME (CoreTrade)
The Contractor shall ensure that the construction personnel comprising the construction
supervisors, tradesmen and/or trade foreman are properly registered under the Construction Registration of Tradesman Scheme (CoreTrade) administered by the BCA and their registration renewed in accordance with Building and Construction Authority (Registration of Construction Personnel) Regulations 2008 including any subsequent changes and re- enactments. The Contractor shall bear all costs, charges and any fees payable arising out of and/or in connection with the CoreTrade scheme including without limitation any time and/or financial penalties that maybe imposed, and/or for compliance with any directions or restrictions ordered by BCA.
C | PERFORMANCE BOND
The Contractor shall within twenty-eight (28) days of the date of Letter of Acceptance submit
a cash deposit or Performance Bond in an amount equal to Ten Percent (10%) of the total Contract Sum (including Prime Cost and Provisional Sums) for the due performance of the Contract under the terms of the Guarantee. The Performance Bond shall be valid for the entire Contract Period including an additional buffer period of six (6) months and the Maintenance Period. The Contractor shall provide the Performance Bond in the format prescribed in Appendix 6. In the event of any extension of time granted under the Contract, or if the Contractor is in default or delay, the validity of the Performance Bond shall be extended accordingly. The cost of obtaining the Performance Bond shall be at the expense of the Contractor and shall be included in the Contract Sum. The Contractor's provision of the cash deposit or Performance Bond shall be a condition precedent to the Contractor's right to receive any progress payment. Any failure to provide the cash deposit or performance bond shall entitle the Employer to withhold all progress payments be due to the Contractor notwithstanding that such progress payments may eventually exceed the Performance Bond amount.
| TO COLLECTION: | $ -
A | INSURANCES
Coverage Period (Contract Period + Six (6) months buffer + Maintenance Period
The insurance shall cover the entire Contract Period, a buffer period of six (6) months and the Maintenance Period. All insurance policies shall be in the joint names of the Employer, Contractor and sub- contractors of any tier. Other than in respect of Work Injury Compensation insurance, the insured Employer, Contractor and sub-contractors shall include their respective directors, officers and employees. Insurance Against Injury To Persons And Property And Work Injury Compensation The Contractor shall provide 'Contractor's All Risks' insurance policy which includes Third Party Liabilities, Workmen's Compensation and Employer's Liability for the Works to cover injuries or damage to persons, any properties caused by collapse, subsidence, vibration, weakening etc. Include but not limited to water leakage to neighbouring house, damages, weakening of structure, etc. The Limit of Indemnity shall be Singapore Dollars: Two Million (S$2,000,000.00) in respect of or arising out of any one occurrence or in respect of or all occurrences of a series consequent upon or attributable to one source or original cause and for unlimited number of claims over the period of insurance. Notwithstanding the stipulated limit of indemnity in any insurance policy, the Contractor shall be liable for and shall indemnify the Employer against any expenses, claim or proceedings, etc. whatsoever in respect of injury or damage to person or properties in the course of carrying out the works. Without limiting the obligations and responsibilities of the Contractor under Clauses 28 of the Conditions of Contract, the Contractor shall effect a Work Injury Compensation Policy and a Contractor's All Risks Policy with an insurance company or companies approved by the Employer’s Representative. The Contractor shall submit the proposed name of the insurance company or companies for consideration of the Employer’s Representative at the time of submission of this tender. The Contractors' All Risks policy shall include Consultants and their authorised representatives as insured parties in respect of their site activities only. The Contractor's All Risks policy shall provide cover in respect of physical loss or damage to the Contract Works on an "all risks" basis and shall also cover the legal liability of the insured parties for accidental damage to third party property and/or accidental bodily injury to third parties arising from the carrying out of the Contract Works.
| TO COLLECTION: | $ -
A | INSURANCES (CONT’D)
Insurance Against Injury To Persons And Property And Work Injury Compensation (cont’d)
The Work Injury Compensation policy shall cover the Contractor and/or all sub-contractors (including designated or nominated sub-contractors) of any tier for their legal liability, whether under the Work Injury Compensation Act or at common law, for death, illness or injury of employees arising in the course of their employment in connection with the carrying out of the Works. The policy shall also cover the Employer’s vicarious liability for whether under the Work Injury Compensation Act or at common law, for death, illness or injury of employees of the Contractor and/or all sub-contractor of any tier arising in the course of their employment in connection with the carrying out of the works. The Contractor's All Risks policy shall provide cover in respect of physical loss or damage to the Contract Works on an "all risks" basis and shall also cover the legal liability of the insured parties for accidental damage to third party property and/or accidental bodily injury to third parties arising from the carrying out of the Contract Works. Insurance of Works The cover for loss or damage to the Contract Works shall be for the full replacement value thereof including all unfixed goods and materials delivered on or adjacent to the Site plus ten (10) percent to cover professional fees and two (2) percent for removal of debris. The cover for legal liability to third parties for accidental property damage and/or accidental bodily injury shall have a limit of liability of $2,000,000.00 any one occurrence with the number of occurrences being unlimited for the period of insurance. The cover under the Contractor's All Risks policy in respect of physical loss or damage shall be extended to include loss or damage to existing property of the Employer caused by the carrying out of the Contract Works on a First Loss basis up to a sum insured of $2,000,000.00. The cover for legal liability to third parties for accidental property damage and/or accidental bodily injury shall include a specific extension acknowledging that representatives of the Building and Workplace Safety and Health Act and/or its Regulations are regarded as third parties under the terms of the insurance policy.
| TO COLLECTION: | $ -
A | INSURANCES (CONT’D)
Endorsements to Insurance
The Contractors' All Risks Policy shall be further extended to include the following endorsements: SECTION I - MATERIAL DAMAGE TO THE WORKS Approved adjusters Strike, Riot and Civil Commotion Time Adjustment Clause (72 hours) Automatic Reinstatement Automatic Extension Cessation of Work - minimum 90 days Extra Charges for Overtime, Nightwork, Work on Public Holidays and Express Freight Escalation/Automatic Increase Clause Removal of Debris Inland Transit Offsite Storage/Fabrication Airfreight Plans and Documents Clause Public Authorities Clause Claims Preparation Clause Free Issue Materials Employees' Personal Effects and Tools Designer's Risks Extended Maintenance Loss Payee SECTION II - LIABILITY TO THIRD PARTY Cross Liability Jurisdiction Clause Non-negligent Indemnity
| TO COLLECTION: | $ -
A | INSURANCES (CONT’D)
Notwithstanding anything contained to the contrary in clause 19(2)(a) of the Conditions of
Contract, the Contractor shall extend the third party liability provision to cover any expense, liability, loss, claim or proceedings which the Employer may incur or sustain by reason of damage to any property other than the Works caused by collapse, subsidence, vibration, weakening or removal of support of lowering of ground water arising out of or in the Course of or by reason of the carrying out the Works excepting damage: a. Caused by negligence, omission or default of the Contractor, his servants or agents or of any sub-contractor, his servant or agents; b. Attributable to errors or omissions in the designing of the Works; c. Which can reasonably be foreseen to be inevitable having regards to the nature of the Works to be executed or the manner of its execution; d. Which is the responsibility of the Employer under the provisions of the Contract; e. Which is recoverable under any other policy of insurance effected for the benefit of the Contractor or Employer; f. Arising from a nuclear risk or a war risk. The limit of liability under this extension in respect of all or any occurrence shall not exceed $2,000,000.00 in the aggregate. The Contractor shall take out and pay all premiums in respect of the above-mentioned insurance policies and any other insurances which he considers to be necessary. Any deductibles/excesses that the Contractor elects to carry is a matter between the Contractor and the insurance company issuing the insurance policy/policies and should be allowed for, as required, when pricing the insurances.
| TO COLLECTION: | $ -
A | QUALIFIED DESIGN PROFESSIONALS
The Contractor shall be fully liable for all acts, omissions and default of such
qualified professionals/persons.
B | DRAWINGS
The drawings identified for this Contract are those issued before the award of the Contract.
The Contractor is deemed to have thoroughly reviewed and understood these drawings prior to submitting his tender. No claims for additional time or costs will be entertained on the grounds of failure to examine the drawings, or due to the issuance of further detailed drawings during the tender period.
| TO COLLECTION: | $ -
The Contractor shall engage suitably qualified design professionals/persons for the purpose of design of the Works and the submissions of applications to the relevant authorities for approval for the design, development, completion, maintenance (during the Maintenance Period) and handing over of the Works. Whenever necessary for the purposes of any application for the relevant permits, licences or approvals from the authorities, the Contractor shall nominate and employ, subject to the Employer's Representative's concurrence (which concurrence shall not be unreasonably withheld), such suitably qualified professionals/persons to carry out, endorse and submit such applications. The Contractor shall not replace such persons concurred by the Employer's Representative as the qualified professionals/persons under these Conditions without the prior Written concurrence of the Employer's Representative (which concurrence shall not be unreasonably withheld), to discontinue the same or to re-appoint and employ another. The Employer's Representative shall have the authority upon reasonable grounds to withdraw his concurrence of the qualified professionals/persons at any time. If such concurrence shall be withdrawn, the Contractor shall, after receiving notice in Writing of such withdrawal, cease to employ or allow the qualified professionals/persons from carrying out any work or undertaking any duties in any capacity with respect to the Contract and shall promptly replace them with qualified professionals/ persons concurred by the Employer's Representative. The Contractor shall be responsible for all arrangements in connection with securing the appointment of the replacement qualified professionals/persons for the Works including obtaining the issue of the Letter of
A | DESIGN AND SHOP DRAWINGS
Before any Works commences in conjunction with the manufacture of any Works, forming
penetration or recesses and installation of any services, the Contractor shall produce full detailed design, shop and co-ordination drawings shown in the proposed locations of all Works, services and any other Sub-contractors’ Works as may be relevant for the purpose of co-ordination Works. The Contractor shall be responsible for any discrepancies, errors or omissions in the design, shop and co-ordination drawings of any Works and other particulars supplied by him, whether such drawings and particulars have been approved by the Employer’s Representative or not. For each submission and/or resubmission of shop drawings, the Contractor shall submit two (2) sets of paper print drawings to the Employer’s Representative for distribution to the Employer and other Consultants for comments.
B | AS-BUILT DRAWING
The Contractor shall submit two (2) sets of paper print 'As Built' drawings prior to issuance of
Handing Over Certificate by the Employer’s Representative. As built drawings shall indicate the setting out and levels of all 'As constructed' buildings on site including all services such as sewer, drainage, roads located within the building site and shall confirm that the overall building height etc are fully complied in accordance with the approved building plans. As-Built drawings for all M&E services (such as Electrical installation, Sanitation and Plumbing, Air Conditioning system, etc.) shall be prepared and endorsed by a licensed Plumber/Electrician and counter-signed by the Contractor before submitting two (2) print copies to the Employer’s Representative. The Contractor shall allow for engagement of a professional photographer designated by the Employer’s Representative for taking as-built photographs of the completed works, such photographs to be taken at different locations and under different lighting conditions, to be agreed by the Employer’s Representative. The Contractor shall submit the as built photographs, of adequate numbers, in both hard and soft copies (in approved format), as directed by the Employer’s Representative.
| TO COLLECTION: | $ -
A | PRECONSTRUCTION SURVEY
The Contractor shall ensure that no damage is caused to the surrounding structures and
neighbouring properties. Before commencement of any works, the Contractor shall undertake a comprehensive pre- construction survey (complying with latest BCA Regulations) of any surrounding land, structures, neighbouring properties, services and the like. The survey shall comprise the following: a. Site layout plan indicating clearly the proposed site and the neighbouring properties; b. Structural and foundation system and the condition of the neighbouring properties; c. Distances of neighbouring properties to the respective nearest pile and/or edge of excavation area; d. Records of defects; e. Extent of cracks; f. Presence of vaults and underground structures; and g. Location of services. The survey report shall include colour photographs dated and suitably captioned. Four (4) sets each of the survey report and photographs shall be supplied to the Employer’s Representative.
B | SETTING OUT OF WORKS
The Contractor shall engage a Licensed Land Surveyor for setting out of the Works including
setting out permanent and temporary bench marks and for establishing all levels accurately. The Contractor shall supply the Employer’s Representative with an 'As set-out- drawings signed by the Licensed Land Surveyor. Upon completion of works, Contractor shall carry out a final survey and submit a final survey plan prepared by the same Licensed Land Surveyor to the Employer’s Representative The final survey plan should indicate all the horizontal and vertical levels of the completed Works including indicating any deviations from the true position of the works. a. 3 copies of certified survey plans b. 2 intermediate prints and softcopy of the drawings in CD c. Setting out of the works within 14 days from Date of Letter of Acceptance. The Contractor shall conduct a preconstruction topographic survey to identify and assess any potential encroachments that may affect the project. This survey will involve detailed measurements and analysis of the existing land features and boundaries within the project area.
C | VERTICALITY/ ALIGNMENT CHECK
The Contractor shall engage a Licensed Surveyor to check and submit survey drawing for
verticality on all columns and beam alignments on every floor.
| TO COLLECTION: | $ -
A | PLANTS, SCAFFOLDINGS, HOIST, ETC.
The Contractor shall provide all necessary plants, scaffolding, hoists, cranes, etc. for the
duration of the Contract and allow for all labour and material for installing, operating, moving, maintaining as necessary and subsequent removal on completion and including fuel and electrical power for their operations. All scaffolding, hoists, cranes, etc. shall be erected to conform with the requirements of the Authorities and in a manner so as not to affect progress of the Works or cause damage to the permanent works.
B | ADJACENT EXISTING STRUCTURES & BUILDINGS' BOUNDARY WALL
The Contractor shall be fully responsible for the full protection & stability of the existing
structures and buildings. The Contractor shall not be entitled to additional payment, compensation, or extension of time in the event of work stoppage by the Ministry of Manpower (MOM) due to safety law violations.
C | SHORING TO ADJACENT BUILDINGS & PROPERTIES
The Contractor shall be responsible for the protection and safety of any adjacent structures by
shoring and other approved methods and materials either driven or placed during or before excavation. Shoring or other approved methods shall be adequately braced and strutted to the satisfaction of the Contractor's Professional Engineer and the temporary works shall be adequately maintained during the period for which it is required so that no damage to the adjacent structures is cause at any time. All shoring and supports shall not be removed upon completion of the Works if their removal endangers the safety of adjacent structures. The Contractor shall ensure a safe working environment on the site at all times. All safety provision shall be properly maintained to the satisfaction of the Employer’s Representative.
| TO COLLECTION: | $ -
A | INTERFERENCE TO TRAFFIC AND ADJOINING PROPERTY
All operations necessary for the execution of the Works and for the construction of any
temporary works shall, so far as compliance with the requirements of the Contract permits, be carried on so as not to interfere unnecessarily or affect the public convenience or the access to use and occupation of public or private roads and footpaths or to, or of properties whether in the possession of the Employer or of any other person and the Contractor shall save harmless and indemnify the Employer in respect of all claims, demands, proceedings, damages and expenses whatsoever arising out of or in relation to any such matters.
B | MAINTENANCE OF EXISTING ROAD, FOOTPATHS, DRAINS, ETC.
The Contractor shall protect and maintain public and private roads, footpaths, culverts, drains,
etc. and keep the approaches to the site clear of mud and debris. The Contractor is to make good any damage attributable to the Works at his own expense or pay all costs in connection therewith.
C | SITE DRAINAGE AND EARTH CONTROL MEASURES
The Contractor shall implement effective Earth Control Measures (ECM) during construction
stage at all times. The ECM shall be implemented according to the Code of Practice on Surface Water Drainage. The Contractor shall note that ECM are meant for the containment and treatment of silty rainwater runoff only, and not meant for the treatment of process water from construction activities such as slurry from tunnelling, pipe-jacking and bore-piling works. Such process water should be handled and treated to comply with the requirements under Environmental Protection and Management Act (Chapter 94A).] The Contractor shall provide schematic diagrams in his tender submission, outlining the ECM for the whole duration of the construction activities, taking into account the various ECM requirements under different phases of construction activities. The ECM plan shall be designed and endorsed by a Qualified Erosion Control Professional (QECP) and form the basis for the Contractor to price for ECM. The Contractor shall be deemed to have included the price of ECM in his tender submission. The Contractor shall engage a QECP to design the ECM. The Contractor shall implement ECM accordingly to the QECP's ECM plan before earth works commence. During the course of construction works, the Contractor shall engage his QECP to review the effectiveness of the ECM regularly, in tandem with the various phases of construction works. The Contractor shall revise the ECM as and when advised by his QECP. The Contractor shall keep good records of the ECM operation and maintenance at all time and shall not remove the ECM until all Works are completed and upon the advice of his QECP. The Contractor shall submit the ECM plan duly endorsed by his QECP to Director, Catchment and Waterways (PUB) to obtain the necessary clearance before commencement of earth works, in the format as prescribed by PUB.
| TO COLLECTION: | $ -
A | EARTH RETAINING OR STABILIZING STRUCTURES (ERSS)
The Contractor shall be responsible for the design, supply, and installation of temporary earth
retaining or stabilizing structures (ERSS), inclusive of the provision of a ground movement and vibration monitoring system, to facilitate the construction of the Works. Prior to the commencement of the Works on site, the Contractor shall appoint a Professional Engineer (PE (Civil)) and a Geotechnical Professional Engineer (PE (Geo)) to prepare and endorse the ERSS design drawings. These endorsed drawings must be submitted to the relevant Authorities for approval. No excavation works shall commence until all approvals for the ERSS submission have been obtained from both the Authorities and the Employer’s Representative. The Contractor shall note that the Employer’s Representative’s approval on the ERSS shall not in any way relieve the Contractor of his responsibilities in the event of failure of the above Works.
| TO COLLECTION: | $ -
A | COST OF TEST
All tests shall be carried out in laboratories accredited by PSB and all reports shall be certified
by the Contractor’s Professional Engineer. If any test is ordered by the Employer’s Representative, the cost of such test shall be borne by the Contractor if the test shows the workmanship or materials not to be in accordance with the provisions of the Contract or the Employer’s Representative's instruction but otherwise by the Employer. Notwithstanding the above mentioned, the cost of carrying out and arranging for all tests listed below and submission of test certificates/reports called for in the Specification shall be borne by the Contractor. a. Hydrostatic tests on concrete flat roofs, toilet floors, kitchen, and external terrace and balconies: - After casting and prior to application of waterproofing membrane or waterproofing screed; - After application of waterproofing membrane or waterproofing screed, and prior to laying of any finishes. - After laying of finishes. b. Hydrostatic tests on pond & water features: - After casting and prior to application of waterproofing membrane; - After application of waterproofing membrane and prior to laying of any finishes; - After laying of finishes. c. Core tests on hardened concrete. d. Non-destructive/destructive tests on hardened concrete. e. Watertightness tests on external brick walls before plastering works. f. Gradient tests to floors of terraces, toilets kitchen and balconies. g. Dye-penetrant/radiographic/ultrasonic tests on welds. h. Watertightness and performance tests on glazed aluminium works. i. Watertightness test on roofing system. The Contractor shall allow here for the cost of complying with all testing and re-testing methods, procedures and requirements to the approval of the Employer’s Representative unless otherwise specifically stated.
| TO COLLECTION: | $ -
A | WORKS WITHIN PUBLIC SEWER CORRIDOR
The Works falls within public sewer corridor defined under Sewerage and Drainage
(Protection of Public Sewerage System) Regulations 2017. The Contractor shall allow for a Professional Engineer to draft and prepare report, CCTV survey, plans and other documents for submission of application under Regulation 5; hire suitable person to supervise and inspect the works; submit declaration and certificate of completion under Regulation 9; and submit further CCTV survey upon completion of works under Regulation 11.
B | OPENING UP PUBLIC ROAD FOR LAYING OF PIPES, ETC.
In the event that the Contractor needs to open up public road to carry out the laying of pipes
etc. then it is the Contractor's responsibility to apply and submit to the various Government Departments applications needed to carry out such works. All fees in connection with the opening up of public road shall be borne by the Employer. The Contractor is to ensure that his insurance company is informed of such works and see to it that his liabilities are fully insured prior to undertaking such works. The Contractor is to note that the relevant Authorities will not normally allow the disturbance of newly surfaced road within a year of surfacing. Upon completion of laying pipes, Contractor shall make good, backfill the trenches with selected earth from own source and compact well, resurface by patching and milling and make good other disturbed works in the surrounding to the satisfaction of the Employer’s Representative and local relevant Authorities.
C | SAFETY, HEALTH AND WELFARE OF WORKMEN
The Contractor shall ensure that all welfare and safety measures required under or by virtue of
the provisions of any enactment or regulations relating to safety, health and welfare of workmen in the construction industry are fully complied with. The Contractor shall allow for complying with Ministry of Manpower's 'Workplace Safety and Health Act' and other relevant Authority's guidelines and recommendations for construction safety for all workmen employed on site by the Contractor, of safety helmets, safety belts, safety boots, safety nets, safety notices, temporary warning lights, etc. and other safety measure, and shall comply with full requirements laid down by other local Authorities or Bye- laws applicable in the Republic.
D | VIDEO SURVEILLANCE SYSTEM
The Contractor shall supply & install video surveillance system (VSS) that covers all higher-
risk work locations and higher-risk work activities (as listed in the Workplace Safety and Health Guide on Video Surveillance Systems ("WSH Guide"). The VSS is a network of cameras, monitors or display units, and recorders used for Surveillance, Identification of workplace safety and health (WSH) risks, Facilitation of incident investigation and corrective actions and deterring unsafe workplace behaviours. The Contractor shall further comply with all guidance and recommendations set out in the prevailing WSH Guide.
| TO COLLECTION: | $ -
A | SITE FIRE PREVENTION
B | SAMPLES & MOCKUP
The Contractor shall submit the following items to Employer’s Representative for approval:
a. Tiles (By Types) b. Railings (All types) c. Ceiling Boards d. Aluminium Roof e. Aluminium Window Section f. Door and architrave (One of each type) g. Ironmongery h. Sanitary Wares, fitting and accessories i. Curtain wall j. Signages k. Aluminium Cladding and Fins l. Textured Paint m. Any other items not mentioned above but are deemed necessary.
C | NOISE AND DUST POLLUTION CONTROL
The Contractor shall ensure strict compliance with provisions under the Environmental
Protection and Management (Control of Noise of Noise At Construction Sites) Regulations including installation of noise monitoring devices under Regulation 4. Access for real time monitoring and record shall be given to the Employer's Representative and National Environmental Agen (NEA). The Contractor shall allow for alternative method of construction at his own expense if the emitted noise levels are above the permissible noise level as set out in the Second Schedule of the Regulation. Any delays or slowdown due to stoppages arising from injunctions or from compliance with any regulatory and mandatory requirement shall be solely at the Contractor's cost and time. The Mechanical plant and equipment which emit excessive noise, smoke, fumes or obnoxious gases will not be allowed to be used on site. The Contractor shall provide adequate dust prevention by spraying, erection of screens or other suitable methods against any nuisance or damage by dust and debris.
| TO COLLECTION: | $ -
The Contractor shall implement fire safety measures for fire prevent and submit a proposal for approval by the Employer and the Employer's Representative. The Contractor shall take all proper and reasonable precautions to control the emission and escape of dust, noise and other pollutants. All plant and equipment shall be fitted with noise suppressors to reduce the level of noise to the permissiable limits. Compressors shall run quietly and be placed away from adjoining premises and peneumatic drills shall be fitted with silencers. The Contractor shall take regular and appropriate measures to abate the nuisance.
A | WORKING UNDER SEVERE HAZE CONDITIONS
B | 24 HOURS CONTACT NUMBER FOR EMERGENCY
The Contractor shall provide 24 hours contact number for emergency and pay all charges in
connection therewith.
C | PROJECT SIGNBOARD
The Contractor shall supply & erect project signboard of size and details as provided by the
Employer’s Representative in compliance with the standard requirements set out by the Building and Construction Authority to a designated location all to Employer’s Representative’s approval. The Project Signboard shall include all the Consultants.
D | TEMPORARY HOARDINGS
The Contractor shall construct temporary hoarding in accordance to Authorities’ requirement.
The hoardings shall include provision of construction access, temporary gates, temporary access, temporary walls, etc. On completion of the works, the hoarding shall be removed from the site and the area made good. The Contractor shall provide noise barrier as specified and indicated in the tender drawing which shall include all the necessary supporting structure, required materials and to ensure the barrier shall function in accordance to the permitted noise requirement.
E | TEMPORARY ACCESS TO SITE
The Contractor shall allow for providing and maintaining all necessary means of access
including temporary bridges if required to the site, paying all fees and charges in connection therewith and for making good disturbed surroundings to the satisfaction of the Employer’s Representative.
F | TEMPORARY BUILDING
The Contractor shall erect temporary buildings, shelter for his own site operations including
storage of materials, equipment, etc. NO worker accommodation on site shall be permitted except for security purpose.
| TO COLLECTION: | $ -
The Contract shall regularly check the 24-hour Pollutant Standards Index (PSI) level make available online by NEA. Healthy persons are to avoid prolonged or strenuous outdoor physical exertion when PSI exceed 200. The Contractor shall review whether outdoor works should continued or reduced for the well-being of the workforce and report his arrangement to the Emplover's Representative. The Contractor shall adhere to Ministry of Manpower's "Guidelines for Employers on Protecting Employees from the Effects of Haze" as part of his primary responsibility for ensuring employee's safety and health at work under Workplace Safety and Health Act.
A | TEMPORARY ELECTRIC POWER AND LIGHTING
The Contractor shall arrange for the necessary supply and electric power and artificial
lightings including all necessary temporary cables, etc. required for the execution of the works and pay all fees and charges in connection therewith and remove on completion of the Works.
B | TEMPORARY WATER SUPPLY
C | TEMPORARY SANITARY ACCOMODATION
The Contractor shall provide temporary sanitary accommodation and allow for free use by all
persons employed including those of Sub-Contractors. Contractor shall keep all these facilities in clean and orderly condition and remove upon completion. D Unless otherwise agreed between the Employer and the Contractor, the water, electricity and gas supply consumed by the Contractor during the Maintenance Period for testing and commissioning of any systems, outstanding Works and rectification of Defects shall be borne by the Contractor. The reimbursement amount of the utility bills to be determined by the Employer’s Representative or the Employer shall be final. The Contractor shall pay/reimburse the Employer accordingly in a mode as stipulated by the Employer.
| TO COLLECTION: | $ -
The Contractor shall arrange for the necessary connection to the Board’s mains and provide, adapt and maintain all temporary pipework, fittings, water storage tanks etc and pay all fees and charges in connection therewith and remove on completion of the Works. UTILITY BILLS OF PERMANENT SUPPLIES USED DURING MAINTENANCE PERIOD
A | CONTRACTOR’S SITE STAFF
The Contractor shall provide adequate and competent site supervisory staff on a full-time
basis for proper execution of the Works which shall include, as a minimum requirement, but not limited to the following: a) A Project Manager with at least a bachelor degree in construction related field and at least 5 years of relevant working experiences. He shall supervise, coordinate and administer all daily works on site throughout the Contract Period. b) Site Supervisor with at least a polytechnic diploma in construction related field with at least 10 years of relevant working experiences. He shall assist the Project Manager to supervise all daily works on site throughout the Contract Period. The Contractor shall additionally provide the following staff on a part time basis for proper execution of the Works which shall include, as a minimum requirement, but not limited to the following: a) A M&E Coordinator with at least a polytechnic diploma in building services engineering or the likes or BCA Academy's Specialist Diploma in M&E Coordination or equivalent with at least 3 years of relevant working experiences. He shall assist the Project Manager to draft the coordinated services plans, supervise, coordinate and administer all daily mechanical, electrical, sanitary and plumbing works on site throughout the Contract Period. The Contractor shall prepare and submit an organisation chart showing a detailed list of his site team for approval by the Employer's Representative. The list shall include all relevant details of each staff member including title, functions, qualification, experience and length of employment with the Contractor. The Contractor shall not replace any staff without giving notice to the Employer's Representative.
B | TRANSPORTATION AND CARRIAGE
The Contractor shall observe and comply with any regulations governing the loading and
unloading of or waiting by vehicles on public roads including special transportation and carriage of any materials, protective covering, warning display and pay all fees and charges. The Contractor shall ensure compliance with the measures implemented by the LTA to enhance the safety of all workers whether directly employed by him or by his sub-contractors. The Contractor shall note and allow for following the guideline titled "Inter-Agency Advisory on Safe Transportation of Workers" issued jointly by Ministry of Manpower, Ministry of Transport, Land Transport Authority, Singapore Police Force and Building and Construction Authority on 31 Dec 2022.
| TO COLLECTION: | $ -
A | SITE OFFICE & MEETING ROOM
The Contractor shall allow in his tender site office & meeting room for Employer’s
supervisory staff & Contractor’s site staff at designated area approved by the Employer’s Representative including all necessary demolition, alteration, partitions, finishings, services, furniture, etc. The Contractor shall pay all costs in connection with the provision of the said facilities including but not limited to power, water, internet, phone bills, consumables etc., maintenance and upkeep of the office in good order and to comply with all local-by-laws and regulations and paying all fees until completion of the contract.
B | PROJECT MEETINGS
The Contractor and the Contractor’s Representatives shall be required to attend all project
meetings called by the Employer’s Representative or the Employer. The project meetings will be held between the Employer’s representatives, the Consultants and the Contractor fortnightly or more as directed by the Employer’s Representative. The purpose of these meetings is to assist in attaining full co-operation in respect of the Works. Minutes of meetings will be recorded and kept by the Employer’s Representative or by such parties as may be directed by Employer’s Representative.
C | WEEKLY REPORTS
The Contractor shall prepare and submit to the Employer’s Representative, weekly reports on
the weather conditions, materials to be delivered to site, number of workmen deployed on site, progress of works by all Sub-contractors and his own progress of works.
D | PROGRESS PHOTOGRAPHS
The Contractor shall submit progress photographs which indicate the location of the works in
progress and date in which this photograph is taken.
E | VERBAL SITE INSTRUCTIONS
The Contractor shall enter all verbal instructions given to him or his representative by the
Employer’s Representative or his representatives in a site instruction log book. He shall record proper description of such instruction and will obtain against each entry the signature of the Employer’s Representative or his representative on the day on which such instructions are given or within seven (7) calendar days of these instructions being given, the Contractor shall send copies of these instructions to the Employer’s Representative for his confirmation. All site instructions shall be copied to the Quantity Surveyor for his information and records.
| TO COLLECTION: | $ -
A | OVERTIME WORKS
The Contractor shall make provisions for overtime payment if he causes his workmen and the
Employer's supervisory staff to work overtime with the written permission of the Employer’s Representative who reserves the right to restrict or prohibit overtime work which results or would result in disturbance to adjoining residents. The Employer shall NOT be responsible for any claims whatsoever in respect of delay or cost in connection with such prohibitions, and no extension of time shall be allowed. For the purpose of this Contract, overtime work shall mean working in one of the following situations: a. Any Sundays or Public Holidays b. Any hour after 12.30pm on Saturdays. c. On weekdays any hour after 5.30pm and before 8.00am the following morning.
B | NO NIGHT OR HOLIDAY WORKS
Subject to any provision to the contrary contained in the Contract, none of the permanent
Works shall be permitted to carry out during the night or on gazetted holidays or rest days without the permission in writing of the Employer’s Representative or his representatives except where work is unavoidable or is absolutely necessary for the saving of life or property, of for the safety of the Works in which case Contractor shall immediately notify the Employer’s Representative or his representatives.
C | INCLEMENT WEATHER
The Contractor shall not be allowed any extension of time due to inclement weather unless
exceptional inclement conditions occur in excess of the following average figures of "Wet Days" return for the last 10 years (2016 - 2025). The "Wet Days" is presumed to be one when rainfall exceeds 10.16mm per day (rainfall records of the 5 Meteorological Service Stations at Paya Lebar, Tengah, Changi, Seletar and Triple One Somerset Building provided by Meteorological Service Singapore). The Contractor shall be required to submit to the Employer’s Representative the actual daily rainfall record from the Meteorological Station nearest to the site to show the increase in the number of Wet Days as compared to the 10-Year Monthly Average Number of Wet Days for the month concerned.
D | PROTECTION OF THE WORKS
The Contractor shall case up and protect all frames, sills and works liable to injury by the sun,
inclement weather, falling debris, etc. and shall take every precaution to protect them against damage from any causes.
| TO COLLECTION: | $ -
A | PEST CONTROL & THERMAL FOGGING
Under the Control of Vectors and Pesticides Act 1998, the Contractor is prohibited from
creating, cause or permit any condition favourable to the propagation or harbouring of vectors. The Contractor shall engage an approved vector control company to undertake regular checks and treatment of the site and the works. The Contractor shall keep and submit records and certificates prepared by the vector control company when requested by the Employer's Representative.
B | WORKS IN CONNECTION WITH SUB-CONTRACTOR
The Contractor shall ascertain from all sub-contractors all particulars relating to their works
with regard to the order of its execution and the position in which chases, holes, mortises and similar items shall be required before the Works are put in hand, as no claim shall be allowed for the extra cost of cutting away Works already executed in consequence of any neglect to ascertain these particulars beforehand.
| TO COLLECTION: | $ -
The Contractor shall allow for any precautions to prevent breeding of mosquitoes and refrain from dumping or depositing rubbish, spoil, unused materials, empty bottles and containers capable of collecting water. All excavations where water stagnates or accumulates shall be kept dry by pumping, bailing or other methods.
A | MATERIALS AND GOOD WORKMANSHIP
All materials, goods and fittings shall be in accordance with the Employer's Requirement
under Appendix 2, other approved drawings, schedules and specifications, the Singapore Standard (SS), British Standard (BS), European Standard (EN) or Code of Practices and/or approved samples, mock ups and catalogues. The Contractor shall ensure all ready-mixed concrete for the Works are obtained from plants which have received certification under the Ready-Mixed Concrete Certification (RMCC) scheme accredited by the Singapore Accreditation Council (SAC). The Contractor shall ensure all relevant products and materials and/or incorporated in the Works have been certified under the Singapore Green Building Product Certification (SGBPC) scheme implemented by the Singapore Green Building Council. Where the SGBPC scheme is not applicable, the Contractor shall comply with the Singapore Green Labelling Scheme (SGLS) administered by the Singapore Environment Council (SEC) or such other eco-labelling schemes as might be specified in the specifications. The Contractor shall allow for tests required under Architect's and Professional Engineer's specifications and shall fully borne the costs of these tests. All test shall be carried out in laboratories accredited by the Singapore Accreditation Council (SAC). A copy of each test shall be forwarded to the Architect, Professional Engineer and Employer's Representative for record. The Contractor shall be responsible for all import and export regulations and shall pay all fees, taxes and charges in connection therewith.
| TO COLLECTION: | $ -
All workmanship relating to the permanent works shall be executed by the skilled workmen and shall be best of their described kinds and shall in all cases be in exact conformity with any specifications and/or described under the Contract. The Contractor shall ensure for fire safety products, only materials that are under SCDF's Product Listing Scheme (PLS) shall be used. These products must be certified by Certification Bodies (CBs) who are accredited by the Singapore Accreditation Council (SAC). The Contractor shall fulfill all documentary requirements e.g. Certificate of Conformity (COC), Declaration of Conformity (DOC), labels, etc required under PLS in order to obtain occupation clearance from SCDF.
A | SITE SECURITY AND PROTECTION OF MATERIALS
The Contractor shall be solely responsible for safeguarding the Works and materials fixed or
unfixed, all equipment and plant on site belonging to him and all Sub-Contractors against damages and theft. He shall affect such necessary additional insurance to adequately cover such risks.
B | WARRANTIES
The Contractor shall provide written warranties including obtaining written warranties
required from Subcontractors and Suppliers and deliver the said warranties to the Employer’s Representative before issuance of the Handing Over Certificate by the Employer’s Representative The Contractor shall submit the following warranties: a. Concrete waterproofing additive for 10 years b. Surface applied waterproofing to roof for 10 years c. Metal roofing for 10 years d. External aluminium windows for 10 years e. Galvanising to metal works for 10 years f. Surface applied waterproofing to internal areas for 10 years g. Stone and tiles adhesives and bonding agents for 5 years h. External painting for 10 years i. Internal emulsion painting for 5 years Warranties shall cover the Employer against all faulty materials and/or workmanship for the periods particularly stated. All warranties periods shall commence from the date of Completion Certificate. Where the Contractor and/or the Sub-Contractors are companies incorporated under the Companies' Act (Cap 50), the Warranty shall be executed on behalf of the company, a company director in the presence of a witness who attests the signature. In addition, the Contractor shall be required to provide and cause the Sub-Contractors to provide a copy of the Board of Directors' resolution confirming that: a. The signatories are the respective company directors, a company director and the company secretary, or a company director of the Contractor and the Sub-Contractor. b. They are/He or she is authorised to execute the Warranty In the event the Contractor fails to execute and submit he required Warranty for any portion of the Works as stipulated under the Contract. The Employer shall be entitled to withhold from any payments due or becoming due to the Contractor an amount equal to ten percent (10%) of the value of the relevant Works.
| TO COLLECTION: | $ -
A | OPERATION AND MAINTENANCE MANUALS
The Contractor shall submit three (3) paper copies and three (3) CD copies of the Operation
and Maintenance (O&M) manuals of all installed system to the Employer within two weeks after obtain TOP. The manuals shall consist least the following information: a. Table of content b. Drawings, single line diagram and schedules c. Directory of companies with contacts d. Manufacturer's technical literature and data e. Operation and maintenance procedures f. Recommendations for preventive maintenance g. Schedule of spares h. Certificates and warranties
B | CLEARING OF DEBRIS
The Contractor shall remove all rubbish from the site as it accumulates from time to time and
upon completion of Contract. In addition, rubbish obstructing fire exits and escape routes shall be removed from the site immediately.
C | CLEARING OF SITE ON COMPLETION
The Contractor shall on completion of all works, clear up and remove from the site all
rubbish, debris, plant, surplus materials, except those materials being the property (under this Contract) of the Employer or those materials ordered to be left on side. Contractor shall remove from site all temporary buildings and site offices, services and the likes, required during the currency of the Contract and clean all polluted areas and leave in a condition as required by the Employer’s Representative.
| TO COLLECTION: | $ -
A | TOUCH UP AND CLEAN PRIOR TO HANDING OVER
The Contractor shall on completion of all works, clear up and remove from the site all
rubbish, debris, plant, surplus materials, except those materials being the property (under this Contract) of the Employer or those materials ordered to be left on side. Contractor shall remove from site all temporary buildings and site offices, services and the likes, required during the currency of the Contract and clean all polluted areas and leave in a condition as required by the Employer’s Representative. Prior to handing over the works and the issuance of the Employer’s Representative's Handing Over Certificate, the Contractor shall thoroughly inspect the Works including touch up all works improperly completed and make good all defects due to bad workmanship or materials, remove all stains, cement droppings, etc. and clean the entire premises to the satisfaction of the Employer’s Representative. The Contractor shall when the works appear to be completed, request the Employer’s Representative to carry out a joint pre-inspection of the works. Such request shall be made in writing to Employer’s Representative at least 7 days prior to the inspection.
B | TEMPORARY OCCUPATION PERMIT (TOP) AND/OR CERTIFICATE
STATUTORY COMPLETION (CSC)
The Contractor shall be responsible for obtaining the Temporary Occupation Permit (“TOP”) and the Certificate of Statutory Completion (“CSC”) on behalf of the Employer. The issuance of the TOP and CSC shall be a condition precedent to the Contractor’s application for the Handing Over Certificate from the Employer’s Representative. The Contractor shall coordinate with all Sub-Contractors and cooperate with the Employer and the Employer’s Representative in connection with any inspections required by the Authorities for the issuance of the TOP and CSC. Such coordination shall include ensuring that the relevant parts of the Works are planned and completed to a stage suitable for inspection and testing by the Authorities, so that the TOP and CSC may be issued without undue delay. The Contractor shall also ensure that all relevant Sub-Contractors are present at every inspection conducted by the Authorities.
| TO COLLECTION: | $ -
SUMMARY FOR PRELIMINARIES
TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE CARRIED FORWARD TO NEXT PAGE: $ -
SUMMARY FOR PRELIMINARIES
BROUGHT FORWARD $ - TOTAL FOR PAGE TOTAL FOR PAGE TOTAL FOR PAGE TOTAL TO GENERAL SUMMARY: $ -
GENERAL SUMMARY (BASE)
BASE TENDER - DEFAULT CONTRACT PERIOD FIXED CONTRACT PERIOD OF - MONTHS ITEM AMOUNT S$ 1 BILL NO. 1 - PRELIMINARIES 2 3 BILL NO. 3A - STRUCTURAL WORKS 4 BILL NO. 3B - MECHANICAL & ELECTRICAL WORKS 5 BILL NO. 3C - ARCHITECTURAL WORKS Signature : Designation : Name of Tenderer : Company Stamp : Date : PROPOSED ADDITIONS AND ALTERATIONS OF AN EXISTING 2-STOREY DETACHED DWELLING HOUSE WITH AN ATTIC ON LOT 99470K MK17 AT 19 CAMBORNE ROAD (NOVENA PLANNING AREA) Eighteen (18) DESCRIPTION TOTAL TENDER SUM CARRIED FORWARD TO FORM OF TENDER: BILL NO. 2 - NAMED SUB-CONTRACTOR, PRIME COST & PROVISIONAL SUMS
GENERAL SUMMARY (ALTERNATIVE)
ALTERNATIVE TENDER - TENDERER'S PROPOSED CONTRACT PERIOD PROPOSED CONTRACT PERIOD OF - MONTHS ITEM AMOUNT S$ 1 BILL NO. 1 - PRELIMINARIES 2 3 BILL NO. 3A - STRUCTURAL WORKS 4 BILL NO. 3B - MECHANICAL & ELECTRICAL WORKS 5 BILL NO. 3C - ARCHITECTURAL WORKS 6 Add/Less : Signature : Designation : Name of Tenderer : Company Stamp : Date : Adjustment for Alternative Contract Period: TOTAL TENDER SUM CARRIED FORWARD TO FORM OF TENDER: PROPOSED ADDITIONS AND ALTERATIONS OF AN EXISTING 2-STOREY DETACHED DWELLING HOUSE WITH AN ATTIC ON LOT 99470K MK17 AT 19 CAMBORNE ROAD (NOVENA PLANNING AREA) DESCRIPTION ___________ ( ) Note: Same as General Summary (Base) Note: Same as General Summary (Base) Note: Same as General Summary (Base) Note: Same as General Summary (Base) BILL NO. 2 - NAMED SUB-CONTRACTOR, PRIME COST & PROVISIONAL SUMS Note: Same as General Summary (Base)